## Gantt chart
Website project: Gantt chart
Project start |  |  | 2026-11-02 | Change this date and the plan moves with it.
Type task names, owners and working days. Start dates chain from the row above; overwrite any of them with a date. End dates skip weekends and the dates on the Holidays sheet. Owner "Client" shades amber; 0 working days = milestone.
[6 empty] | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 5 | Wk 6 | Wk 7 | Wk 8 | Wk 9 | Wk 10 | Wk 11 | Wk 12 | Wk 13 | Wk 14 | Wk 15 | Wk 16
Phase | Task | Owner | Start | Working days | End
Discovery | Kickoff workshop | Agency |  | 2
Discovery | Stakeholder interviews | Agency |  | 4
Discovery | Sitemap and content plan | Agency |  | 5
Discovery | Discovery sign-off | Client |  | 0
Design | Wireframes | Agency |  | 7
Design | Visual design | Agency |  | 8
Design | Design feedback | Client |  | 4
Design | Design approved | Client |  | 0
Build | Development | Agency |  | 14
Build | Content entry | Client |  | 8
Launch | QA and testing | Agency |  | 5
Launch | Go live | Agency |  | 0

## Holidays
Date | Name | Replace these with your own public holidays and shutdown days. End dates skip anything listed here.
2026-12-25 | Christmas Day
2026-12-28 | Boxing Day (observed)
2027-01-01 | New Year's Day

## How it works
How this template works
Start: the first task starts on the project start date. Other rows use WORKDAY() to start the working day after the row above finishes (or alongside it). Type a date over any formula to fix it.
Working days: how long the task takes, excluding weekends and the dates on the Holidays sheet. 0 makes the row a milestone (a diamond).
End: =WORKDAY(Start, Working days - 1, Holidays). To count working days between two dates you already have, use =NETWORKDAYS(Start, End, Holidays).
Different weekend? Swap WORKDAY for WORKDAY.INTL, e.g. =WORKDAY.INTL(D6,E6-1,7,Holidays) for a Friday-Saturday weekend.
Bars: the week grid is shaded by conditional formatting. A week is shaded if the task runs during any part of it. Owner "Client" shades amber.
Adding rows: use the blank formatted rows under the sample, or insert rows inside the task list so the formatting range grows with them.
Longer projects: copy the last week column to the right. The conditional formatting applies to the grid range; extend it under Conditional Formatting > Manage Rules if needed.
Guide: https://neogantt.com/guides/gantt-chart-excel